## Sheet1
Task	Activities	input required
ROAR Mapping	Downloaded files from ROAR (2011, 2010, 2008)
	Prepared files manually (-raw)
	Cleaned files (-clean): do files
	Mapping 2010: Compared mapping 2010 to online ROAR 2010 -do file	feedback on results
	Mapping 2010: Compared all results in mapping with STATA calculations based on mapping data (description, tabulation, graphics) - do file	feedback on results
	Mapping 2011: Selected newly added projects in 2011 - do file	review
	Mapping 2011: Selected active projects - do file	review
	Mapping 2011: Prepared merge with country classifications - do file	decision on ISO vs UNDP naming conventions
Mobile case study	Researched youth participation in Madagascar
	Drafted chapters: context (country, ICT), issues (parts)	feedback
	Reviewed documents received
	Drafted parts of chapter project description	feedback
	Defined areas that require further input and formulated specific questions
	Requested interview with UNDP Madagascar
Mobile issue brief	Clarified first approach in team (RKS and SL)
	Started research on social innovation and mobile technology
Data repository	Merged data that had been agreed to be added	review
	Exchanged correspondence with social media data providers (ongoing)
Mobile contacts	Attended 2 UNICEF presentations	feedback on Plan International's interest in local governance & innovation
Admin	Administrative tasks	submission